## Sheet1
Gantt Chart for Times Table Game | date | date | date | date | Date due | Future
SD Stages of Development
Defining & Understanding the problem | 24/7/23 | 25/7/23 | Done | Done | 25/7/2023
Client Requirements | 24/7/23 | 25/7/23 | Done | Done | 24/7/2023
Enquiring into Existing solutions | 24/7/23 | 25/7/23 | Done | Done | 24/7/2023
Planning & Designing a solution | 25/7/23 | 23/7/23 | Done | Done | 28/7/2023
IPO Chart | 24/7/23 | 27/7/23 | Done | Done | 25/7/2023
Context Diagram | 25/7/23 | Done | Done | Done | 25/7/2023
Data flow Diagram | 25/7/23 | Done | Done | Done | 25/7/2023
Implementing the solution | 27/7/23 | 31/7/23 | 2023-01-08 | 2023-03-08 | 2023-04-08
Menu System | 2023-03-08 |  |  |  | 31/7/2023 | Scoring system delayed work on this module.
Help file |  |  |  |  | 31/7/2023 | Working on the main functionality before writing the help file
Answering system |  |  |  |  | 2023-02-08
High score system | 27/7/23 | 31/7/23 | Done | Done | 2023-02-08
Timing system |  |  |  |  | 2023-03-08
Difficulty system |  |  |  |  | 2023-01-08 | Scoring system delayed work on this module.
Testing & Evaluating the solution |  |  |  |  | 2023-08-08
Maintaining the solution |  |  |  |  | 2023-10-08